## How to use
Weekend 2.0 — Project Tracker
Created | 2026-10-02 (IST). Source of truth is PROJECT_MEMORY.md; this workbook is a working view of it.
Cells to edit | Yellow-shaded cells are inputs: status, dates, notes, final choices, cost figures. Do not edit white formula cells.
Add a row | Type in the next empty row of Tasks / Issues / Decisions / Approvals. Dashboard and Phases update automatically (rows 2–200).
Task / Phase status | Not started · In progress · Blocked · Done (pick from the dropdown).
Decision status | Open · Provisional · Decided. Decide in order D1 → D2 → D4 → D5 → D6 → D3.
Issue severity | Critical · High · Medium · Low. Status: Open · Closed.
Dates | Format yyyy-mm-dd (IST).
Cost sheet | Blue numbers are inputs from DESIGN.md §21 (prices checked 2026-10-02). INR is calculated from the exchange-rate cell. Re-check 'Not verified' rows in the AWS Pricing Calculator.
Update routine | After each working session: update Tasks/Issues here, then run `save project` so PROJECT_MEMORY.md matches.
Rules | No secrets, account IDs or real IPs in this workbook.

## Dashboard
Weekend 2.0 — Project Dashboard
Project start | 2026-10-02
Days since start
Tasks
Total tasks
Done
In progress
Blocked
Not started
Overall % done
Critical tasks not done
Phases
Phase | Status | Tasks done %
Decisions (D1 → D2 → D4 → D5 → D6 → D3)
Open
Provisional
Decided
Next decision
Open issues by severity
Critical
High
Medium
Low
Total open
Cost vs budget (monthly)
Estimated cost (₹)
Budget (₹)
Headroom (₹)
Budget used
Fits budget?
Note on B2: Project start date (from PROJECT_MEMORY.md M1).

## Phases
Phase | Name | Exit criteria | Status | Start | Target | Done | Evidence | Tasks done % | Tasks (done / total)
0 | Requirements & architecture | D1–D4 decided; diagram and cost estimate approved | In progress | 2026-10-02 |  |  | DESIGN.md v0.1.3; diagrams 01–05; READMEs
1 | MVP backend | Agent core answers via a test interface, with unit tests | Not started
2 | Mobile access | Owner uses it from the phone securely (D6, TLS) | Not started
3 | Memory & storage | Encrypted, owner-controlled memory with retention, export, delete | Not started
4 | Security hardening | Threat model done; P1–P10 verified in M7 | Not started
5 | CI/CD & IaC | All infra in Terraform; pipelines build, test, deploy | Not started
6 | Monitoring & ops | Logs, alerts, backups; restore tested | Not started

## Tasks
ID | Phase | Task | Priority | Status | Start | Due | Done | Notes
T-001 | 0 | Audit Weekend v1 and list unneeded files | Medium | Done | 2026-10-02 |  | 2026-10-02 | Cleanup list delivered
T-002 | 0 | Research 2026 prices and options | High | Done | 2026-10-02 |  | 2026-10-02 | Sources in DESIGN.md Appendix C
T-003 | 0 | Draft DESIGN.md | High | Done | 2026-10-02 |  | 2026-10-02 | Now v0.1.3
T-004 | 0 | Set monthly budget (₹5,000) | High | Done | 2026-10-02 |  | 2026-10-02 | BUD-20261002
T-005 | 0 | Project README + docs README | Medium | Done | 2026-10-02 |  | 2026-10-02
T-006 | 0 | Architecture diagrams (FigJam + docs/diagrams) | Medium | Done | 2026-10-02 |  | 2026-10-02 | 5 diagrams: jpg/svg/mmd
T-007 | 0 | Update PROJECT_MEMORY (save project) | Medium | In progress | 2026-10-02 |  |  | Diff awaiting owner approval
T-008 | 0 | Verify 'Not verified' Mumbai prices (I-3) | High | Not started |  |  |  | AWS Pricing Calculator
T-009 | 0 | Decide D1 (hosting) | High | Not started
T-010 | 0 | Decide D2 (AI model) | High | Not started |  |  |  | Depends on D1
T-011 | 0 | Decide D4 (cloud provider) | High | Not started |  |  |  | Depends on D1, D2
T-012 | 0 | Approve architecture diagram + cost estimate (Phase 0 exit) | High | Not started
T-013 | — | Rotate leaked Weekend v1 tokens (I-1) | Critical | Not started |  |  |  | Then purge or archive the old repo
T-014 | 0 | Claim the FigJam board (I-6) | Low | Not started
T-015 | 1 | git init + private GitHub repo (needs approval) | Medium | Not started

## Decisions
ID | Order | Decision | Status | Provisional recommendation | Final choice | Date decided | ADR file
D1 | 1 | Hosting | Open | Private EC2 server, ap-south-1, tailnet-only (DESIGN §17)
D2 | 2 | AI model | Open | Claude Haiku 4.5 + Sonnet 5 via Bedrock India profile (§7)
D4 | 3 | Cloud provider | Open | AWS (§16)
D5 | 4 | Storage / hardware | Open | PostgreSQL 17 + pgvector on encrypted EBS (§9)
D6 | 5 | Authentication | Open | Tailnet + passkey (§14)
D3 | 6 | Mobile interface | Open | PWA (§15)

## Issues
ID | Description | Severity | Owner action | Status | Opened | Closed
I-1 | Leaked tokens in Weekend v1 git history | High | Rotate tokens; purge or archive the old repo | Open | 2026-10-02
I-2 | Bedrock Sonnet 5 price conflict ($2/$10 vs $3/$15) | Low | Check the AWS Bedrock pricing page | Open | 2026-10-02
I-3 | Several Mumbai prices 'Not verified' | Low | Refresh with the AWS Pricing Calculator before D1 | Open | 2026-10-02
I-4 | Voice options exceed the ₹5,000 budget at today's prices | Medium | Evaluate DESIGN §21.4 options in Phase 2 | Open | 2026-10-02
I-5 | AWS network diagram shows WireGuard as one-way arrows | Low | Optional: fix in FigJam and re-export 04 | Open | 2026-10-02
I-6 | FigJam board is an unclaimed Claude draft; seat is 'View' | Low | Claim the board in Figma | Open | 2026-10-02

## Cost
Item | Basis | USD / month | INR / month | Verified? | Source
EC2 t4g.medium | $0.0224/h × 730 h | 16.35 |  | sparecores.com (2026-10-02)
EBS gp3 40 GB | ~$0.09/GB-month | 3.6 |  | Estimate — check AWS Pricing Calculator
Public IPv4 | $0.005/h × 730 h | 3.65 |  | Estimate — check AWS Pricing Calculator
KMS customer-managed keys | 2 keys × $1 | 2 |  | Estimate — check AWS Pricing Calculator
Secrets Manager | 5 secrets × $0.40 | 2 |  | Estimate — check AWS Pricing Calculator
S3 backups + Object Lock | ~15 GB + requests | 0.6 |  | DESIGN.md §21.2
EBS snapshots | Weekly, incremental | 1 |  | DESIGN.md §21.2
CloudWatch Logs | < 1 GB/month | 1 |  | DESIGN.md §21.2
Tailscale | Personal plan | 0 |  | ssdnodes.com (2026-10-02)
LLM — Bedrock India (expected, 3,000 turns) | 80% Haiku 4.5 / 20% Sonnet 5, +10% regional | 15.9 |  | DESIGN.md §21.1; platform.claude.com pricing
Total per month
Exchange rate (₹ per USD) | 96.3 | Mid-market, 2026-10-02, tradingeconomics.com
Monthly budget (₹) | 5000 | Set by owner 2026-10-02 (BUD-20261002)
Headroom (₹)
Budget used
Fits budget?
Scope: text-only, Option B (private EC2 + Bedrock). Voice adds ≈ ₹1,580 (local) or ≈ ₹3,040 (AWS) — see DESIGN.md §21.3–21.4.

## Approvals
Date | Action | Target | Risk | Approved by
2026-10-02 | Send architecture design (no secrets/personal data) to Figma | Figma Inc. (FigJam) | Low | Owner

## Doc versions
Document | Version | Date | Type | Summary
DESIGN.md | 0.1.0 | 2026-10-02 | Initial draft | Base plan: architecture, components, cost model, roadmap
DESIGN.md | 0.1.1 | 2026-10-02 | Patch | Budget set to ₹5,000/month; budget fit added
DESIGN.md | 0.1.2 | 2026-10-02 | Patch | FigJam board link; data exit X8 (Figma)
DESIGN.md | 0.1.3 | 2026-10-02 | Patch | Diagram images added (docs/diagrams/: jpg, svg, mmd)